## Pivot tables
Row Labels | Count of TYPE OF Error | Row Labels | Count of DETAILS OF Error OCCURRED | Row Labels | Count of TYPE OF Error | Row Labels | Count of TYPE OF Error | Row Labels | Count of TYPE OF Error | Row Labels | Count of TYPE OF Error
2023 | 30 | APH | 1 |  | 1 |  | 1 | January | 6 | January | 6
2024 | 113 | BAG FILTER | 4 | Bendness | 1 | Bendness | 1 | February | 11 | Grand Total | 6
Grand Total | 143 | BOILER | 80 | Crack | 1 | Crack | 1 | March | 9
|  | BOILER | 1 | Crater | 1 | Crater | 1 | April | 11
|  | BOILER (RSO) | 1 | Cutting | 1 | Cutting | 1 | May | 8
|  | BOX COVER PLATE | 1 | DIAL OF PREESURE GUAGE WAS BLACKISH | 1 | DIAL OF PREESURE GUAGE WAS BLACKISH | 1 | June | 17
|  | CABINET | 1 | Drawing | 9 | Drawing | 9 | July | 8 | Row Labels | Count of TYPE OF Error
|  | CHIMNEY | 2 | Fitup | 9 | Fitup | 9 | August | 5 | January | 6
|  | COIL BOTTOM REDUCER | 1 | Incoming | 5 | Incoming | 5 | September | 1 | Grand Total | 6
|  | COIL TYPE BOILER | 6 | Insulation Sheet | 1 | Insulation Sheet | 1 | November | 1
|  | CONTROL PANEL | 1 | Lack of fusion | 1 | Lack of fusion | 1 | December | 3
|  | CORROGATIVE SHEET | 1 | Leakage | 2 | Leakage | 2 | Grand Total | 80
|  | CRS | 1 | Marking | 71 | Marking | 71 |  |  | Row Labels
|  | DARIATION TANK | 1 | Mismatch | 1 | Mismatch | 1 |  |  | 2023
|  | DUCTING | 1 | Nozzle orientation | 1 | Nozzle orientation | 1 | Row Labels | Count of TYPE OF Error | Grand Total
|  | ECONOMISER | 3 | Pin holes & Spatters | 1 | Pin holes & Spatters | 1 | 1005 | 1
|  | ELECTRODE | 2 | Pitted & Broken | 1 | Pitted & Broken | 1 | 1009 | 1
|  | ERW TUBE | 2 | Poor Weld Finishing | 3 | Poor Weld Finishing | 3 | 1011 | 1
|  | FEED WATER TANK | 1 | Porosity | 8 | Porosity | 8 | 1014 | 2
|  | FEED WATER TANK | 1 | Production | 5 | Production | 5 | 1016 | 3
|  | FURNACE ENCLOSER | 1 | Purchase | 8 | Purchase | 8 | 1017 | 3
|  | FURNACE ENCLOSR | 1 | Rolled | 1 | Rolled | 1 | 1019 | 1
|  | FURNACE TOP PLATE | 1 | Rusted | 1 | Rusted | 1 | 1020 | 1
|  | FWT | 1 | Short width | 1 | Short width | 1 | 1022 | 1
|  | HEX BAR | 1 | Slag | 1 | Slag | 1 | 1024 | 3
|  | HOT AIR GENERATOR | 1 | Spatter | 1 | Spatter | 1 | 1026 | 1
|  | HOT WATER GENERATOR | 4 | Uneven Height of Electrode | 1 | Uneven Height of Electrode | 1 | 1034 | 1
|  | I BEAM | 1 | Welding | 4 | Welding | 4 | 1043 | 1
|  | MEMBRANE | 1 | Wrong deliverd | 1 | Wrong deliverd | 1 | 1047 | 1
|  | MS PLATE | 1 | Grand Total | 143 | Grand Total | 143 | 1048 | 66
|  | MS SOCKET | 1 |  |  |  |  | 1057 | 1
|  | O CLAMP | 1 |  |  |  |  | 1065 | 1
|  | OIL TANK | 2 |  |  |  |  | 486 | 1
|  | PIPE | 1 |  |  |  |  | 555 | 1
|  | PRESSURE GAUGE | 1 |  |  |  |  | 784 | 1
|  | PRESURE GUAGE | 1 |  |  |  |  | 810 | 1
|  | PRS | 1 |  |  |  |  | 888 | 2
|  | PULLY 3.5" 90 OD | 1 |  |  |  |  | 901 | 7
|  | ROUND BAR | 1 |  |  |  |  | 906 | 1
|  | SQ. BAR | 1 |  |  |  |  | 912 | 3
|  | STOCK | 1 |  |  |  |  | 914 | 1
|  | STRUCTURE | 1 |  |  |  |  | 915 | 1
|  | THERMIC FLUID HEATER | 2 |  |  |  |  | 920 | 3
|  | TUBE PLATE | 1 |  |  |  |  | 928 | 1
|  | WATER TANK | 1 |  |  |  |  | 930 | 2
|  | WPH | 1 |  |  |  |  | 941 | 1
|  | Grand Total | 143 |  |  |  |  | 948 | 1
[8 empty] | 960 | 1
[8 empty] | 968 | 4
[8 empty] | 969 | 1
[8 empty] | 972 | 3
[8 empty] | 980 | 1
[8 empty] | 994 | 4
[8 empty] | GN824 | 3
[8 empty] | STOCK | 10
[8 empty] | Grand Total | 143

## DashBoard
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
QUALITY CONTROL DASHBOARD
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Clean Data
SN | DATE | ORF | NAME OF EQUIPMENT/ PART | TYPE OF Error | DETAILS OF Error OCCURRED | ROOT CAUSE OF Error OCCURRED | CORRECTIVE ACTION | Year | Month | Month Name
1 | 2023-06-03 | 901 | BAG FILTER | Porosity | Porosity Defect Found In Corner Joint Of Bag Filter | Lack Of Awarness Of Welder | Eliminated | 2023 | 6 | June
2 | 2023-06-03 | 912 | BOILER | Porosity | Porosity Defect Found In Corner Side Of Boiler | Lack Of Awarness Of Welder | Eliminated | 2023 | 6 | June
3 | 2023-06-03 | 912 | BOILER | Lack of fusion | Lack Fusion Found Assmebly Of Boiler Shell & Smoke Box | Lack Of Awarness Of Welder | Eliminated | 2023 | 6 | June
4 | 2023-06-03 | 901 | BOILER | Porosity | Porosity Defect Found In Corner Of Smoke Box | Lack Of Cleaning Of Weld Joint Before Welder | Eliminated | 2023 | 6 | June
5 | 2023-06-03 | 901 | BOILER | Poor Weld Finishing | Poor Weld Finshing In Nozzles Support Stiffner | Wrong Technique Applied By Welder | Eliminated by gring and welding | 2023 | 6 | June
6 | 2023-06-08 | 901 | BOILER | Porosity | Porosity Defect Found In Welding Of Flat With Membrane Tube | Lack Of Awarness Of Welder | Removed | 2023 | 6 | June
7 | 2023-06-08 | 901 | BAG FILTER | Crack | Found Crack Corner Of Bag Filter To Joint Angle | Lack Of Awarness Of Fitter | Eliminated | 2023 | 6 | June
8 | 2023-06-12 | 888 | BOILER | Crater | Some Crater Was Found On The Bollier Shell | Lack Of Awarness Of Welder | Eliminated | 2023 | 6 | June
9 | 2023-06-19 | 920 | COIL TYPE BOILER | Porosity | Porosity Was Found On The Coil | Lack Of Awarness Of Welder |  | 2023 | 6 | June
10 | 2023-06-27 | 784 | THERMIC FLUID HEATER | Slag | Slag Was Found Joint Of Shell | Lack Of Awarness Of Welder | Eliminated | 2023 | 6 | June
11 | 2023-06-09 | STOCK | PRESSURE GAUGE | Wrong deliverd | Recived 6"+600 Mmwc In Placed Of-0 To-600Mmwc | Lack Of Awarness Of Vendor | Rejeted | 2023 | 6 | June
12 | 2023-06-13 | 888 | BOILER | Poor Weld Finishing | Poor Weld Finshing In Support Of Header | Lack Of Awarness Of Welder | Eliminated | 2023 | 6 | June
13 | 2023-06-14 | 912 | BOILER | Poor Weld Finishing | Poor Weld Finshing In Weld Joint | Lack Of Awarness Of Welder | Eliminated | 2023 | 6 | June
14 | 2023-07-08 | 901 | BAG FILTER | Spatter | Found Spatter On The Side Of The Bag Filter | Lack Of Awarness Of Welder | Eliminated | 2023 | 7 | July
15 | 2023-07-11 | 920 | COIL TYPE BOILER | Porosity | Porosity Was Found On The Coil Weld Area | Lack Of Awarness Of Welder | Eliminated | 2023 | 7 | July
16 | 2023-07-11 | 906 | HOT AIR GENERATOR | Insulation Sheet | Insulation Sheet Was Damaged And Not Fitted Properly | Production | Eliminated | 2023 | 7 | July
17 | 2023-07-16 | 901 | FEED WATER TANK | Porosity | 40 Nb Nozzles To Shell Welding Found Leaked During Water Filling Test At One Point Due To Porosity In Welding. | Lack Of Awarness Of Welder | Eliminated | 2023 | 7 | July
18 | 2023-07-21 | STOCK | STOCK | Pitted & Broken | 5 Ci Wheels Are Found Pitted & Broken | Lack Of Awarness Of Vendor | 5 Nos are Rejected | 2023 | 7 | July
19 | 2023-07-25 | 941 | COIL TYPE BOILER | Pin holes & Spatters | In Coil1 & Coil 2 Some Pin Holes & Spatters Were Found On The Coils | Lack Of Awarness Of Welder |  | 2023 | 7 | July
20 | 2023-07-27 | 914 | BOILER | Porosity | Orf-914, During Hydro Test, Found Leakage In 4 Tube Of Boiler Due To Small Porosity On The Corner Of Weld | Lack Of Awarness Of Welder | Eliminated | 2023 | 7 | July
21 | 2023-08-14 | 948 | ERW TUBE | Production | Dent Was Found Is Only One Erw Tube, It Is Not Acceptable | Lack Of Awarness Of Vendor | Rejected | 2023 | 8 | August
22 | 2023-08-09 | 486 | ERW TUBE | Production | During Filling Water, Found Leakage In 1 Tube Of Boiler Due To Small Porosity On The Corner Of Weld | Lack Of Awarness Of Welder | Eliminated | 2023 | 8 | August
23 | 2023-08-11 | 555 | BOILER | Drawing | The Hole Distance From The Center Of The Smoke Box Is Given As 115 Mm In The Drawing But In The Actualjob It Is 95Mm | Drawing Mistake | - | 2023 | 8 | August
24 | 2023-08-19 | STOCK | COIL TYPE BOILER | Purchase | 12.7 Mm Dia Spring Was Required As Per Po, But 9.5Mm Dia Spring Was Recived, Qty- 06 Nos | Lack Of Awarness Of Vendor | Rejected | 2023 | 8 | August
25 | 2023-08-19 | 928 | BAG FILTER | Purchase | 25 Mm Weld Socket Was Required As Per Po, But 25 Mm Threaded Socket Was Recived Qty- 30 Nos | Lack Of Awarness Of Vendor | Rejected | 2023 | 8 | August
26 | 2023-09-08 | 810 | THERMIC FLUID HEATER | Purchase | 65 Nb Short Bend Was Found Pitted, Bented And Dirty (10 Nos) | Lack Of Awarness Of Vendor | Rejected | 2023 | 9 | September
27 | 2023-11-08 | STOCK | PRESURE GUAGE | DIAL OF PREESURE GUAGE WAS BLACKISH | H-Guru Made Presure Guage (0-42 Kg/Cm2) Qty=1 Dial Of Presure Guage Was Blackish And Not Acceptable | Lack Of Awarness Of Welder | REJECTED | 2023 | 11 | November
28 | 2023-12-15 | 969 | ECONOMISER | Welding | During The Inspection Of Econimozer Structure Shell Weling Found Errorin L-Seam Welding | Welder Negligance | ELIMINATED | 2023 | 12 | December
29 | 2023-12-15 | STOCK | O CLAMP | Purchase | 40 Mm Dia O Clamp Was Required But Recieved 32 Mm Dia | Lack Of Awarness | REJECTED | 2023 | 12 | December
30 | 2023-12-26 | 972 | BOILER | Production | Boiler Tube Welding Leak Found During Hydro Test Inspection | Welder Negligance | ELIMINATED | 2023 | 12 | December
31 | 2024-01-01 | 972 | FURNACE ENCLOSER | Drawing | Furnace Encloser Of Front Side Of Boiler Given Wrong Design In Drawing . | Lack Of Awarness Of Drawing Dept. | ELIMINATED | 2024 | 1 | January
32 | 2024-01-02 | 915 | MEMBRANE | Drawing | Boiler Water Wall Top Header Hole To Hole Distance For Tube Fitting Is Given Wrong By Drawing Dept. | Lack Of Awarness Of Drawing Dept. | ELIMINATED | 2024 | 1 | January
33 | 2024-01-04 | 994 | TUBE PLATE | Drawing | Tube Plate Hole Drill Diameter Was Not Given In Drawing | Drawing Dept. Negligance | ELIMINATED | 2024 | 1 | January
34 | 2024-01-06 | 980 | OIL TANK | Welding | Top Side Plate Of Oil Tank Is Sweeled Due To Wrong Fittment | Lack Of Awarness Of Fitter | REWORK | 2024 | 1 | January
35 | 2024-01-10 | STOCK | MS PLATE | Purchase | Ms Plate (Lxbxt)=(6300X1515X6 Mm Thk) Was Bend At Many Points . | Vendor Negligance | REJECTED | 2024 | 1 | January
36 | 2024-01-11 | STOCK | CORROGATIVE SHEET | Purchase | Corrogative Sheet Is Scratched At Many Points. | Vendor Negligance | REJECTED | 2024 | 1 | January
37 | 2024-02-01 | STOCK | ECONOMISER | Cutting | Economizer Nozel Hole Cutting Was Not As Per Drawing | Negligance | ELIMINATED | 2024 | 2 | February
38 | 2024-02-07 | 1009 | BOILER (RSO) | Production | Thermostat Pipe Was Welded Deep Inside The Outlet Pipe | Lack Of Knowlwdge | ELIMINATED | 2024 | 2 | February
39 | 2024-02-07 | 994 | FURNACE ENCLOSR | Drawing | Furnace Enclozer Length Was Given In Drawig 40 Mm Extra | Mis Calculation Of Drawing | REWORK' | 2024 | 2 | February
40 | 2024-02-07 | 994 | BOILER | Drawing | Leg Height Of Boiler Was Given Wrong In Drawing Required =1215 But Given In Drawing =1315 | Mis Calculation Of Drawing | ELIMINATED | 2024 | 2 | February
41 | 2024-02-12 | 972 | FURNACE TOP PLATE | Drawing | Length Of Furnace Top Plate Was Given Wrong In Drawing Required =1544 But Given In Drawing =1500 | Mis Calculation Of Drawing | REWORK | 2024 | 2 | February
42 | 2024-02-12 | 968 | BOX COVER PLATE | Production | Tirminal Box Cover Plate Was Damaged | Production Negligance | REWORK | 2024 | 2 | February
43 | 2024-02-12 | 1005 | PRS | Drawing | Prv Connection Flange Given In Drawing Was =Class 300 But Required =Class 150 | Drawing | REWORK | 2024 | 2 | February
44 | 2024-02-12 | STOCK | MS SOCKET | Purchase | Ms Socket Rejected Due To Rusted From Outside And Inside | Vendor Negligance | REJECTED | 2024 | 2 | February
45 | 2024-02-13 | STOCK | PULLY 3.5" 90 OD | Purchase | Pully Rejected Due To Outer Dia Was Not Matched Required Outer Dia =90 But Observed Outer Dia =84 | Vendor Negligance | REJECTED | 2024 | 2 | February
46 | 2024-02-20 | 994 | BOILER | Welding | Welder Left The Welding In Saddle To Shell Joint | Welder Negligance | ELIMINATED | 2024 | 2 | February
47 | 2024-02-26 | 960 | BOILER | Drawing | Feed Line Of Boielr Shell Given 40Mm Extra In Drawing | Mis Calculation Of Drawing | ELIMINATED | 2024 | 2 | February
48 | 2024-03-12 | 968 | HOT WATER GENERATOR | Mismatch | Rockwool Pad Batch Number Mismatched From Mtc | Mis Typing By Vendor | Elimated | 2024 | 3 | March
49 | 2024-03-13 | 968 | HOT WATER GENERATOR | Leakage | During Hydro Testing Of Heat Water Generator Found 05 Heater Element Leakage. | Poor Brazzing Welding | Replaced to vendor | 2024 | 3 | March
50 | 2024-03-15 | 968 | HOT WATER GENERATOR | Leakage | During Hydro Testing Of Heat Water Generator Found 03 Heater Element Leakage. | Poor Brazzing Welding | Replaced to vendor | 2024 | 3 | March
51 | 2024-03-16 | 1019 | FEED WATER TANK | Marking | During Inspection Of Nozzle Marking Found 15Nb Socket Marking Missing In Front Of Tank . | Proper Did Not Check Drawing | Remarking | 2024 | 3 | March
52 | 2024-03-18 | 1022 | BOILER | Marking | Width Of Furnace Shell Plate Beyond Upto 08Mm As Per Drawing. | Production Negligance | Rework | 2024 | 3 | March
53 | 2024-03-22 | 1011 | WATER TANK | Fitup | Saddle Centre To Centre Distance Beyond Upto 12Mm As Per Design | Production Negligance | Warn to fitter | 2024 | 3 | March
54 | 2024-03-23 | 1020 | COIL TYPE BOILER | Fitup | Optimiser Flange Under Thickness Fittted Need 14Mm Thick Flange But Fitted 12Mm Thick. | Production Negligance | Warn to fitter | 2024 | 3 | March
55 | 2024-03-28 | 1014 | APH | Fitup | Baffle Of Mddle Shell Of Aph Fitted In Opposite Tube Plate That Reason Orientation Of Hole Are Not Matched As Per Drawing . | Production Negligance | Warn to fitter | 2024 | 3 | March
56 | 2024-03-28 | 1014 | DARIATION TANK | Fitup | Fluid Inlet Flange Is Not In Level And Also Projection Of Flange Short Upto 05 Mm . | Production Negligance | Warn to fitter | 2024 | 3 | March
57 | 2024-04-01 | 1034 | CHIMNEY | Incoming | Lot Of Rust Occured On Pipe Of Chimney ,Size Is 200Nb | Vendor Negligance | Warn to Purchase | 2024 | 4 | April
58 | 2024-04-05 | 1016 | COIL BOTTOM REDUCER | Rolled | We Need Ø1311 Mm Od But We Find Out Ø1105Mm And Bottom Side We Need Ø580Mm But We Find Out Ø412Mm. | Layout Showing In Drawing Is Wrong . | Warn to Design Team | 2024 | 4 | April
59 | 2024-04-05 | 1016 | I BEAM | Incoming | I Beam Received Upto 10Mm Bend.. | Vendor Negligance | Warn to Purchase | 2024 | 4 | April
60 | 2024-04-09 | 1026 | CONTROL PANEL |  | Panel Back Hole Out Upto 10Mm | Vendor Negligance | Warn to Purchase | 2024 | 4 | April
61 | 2024-04-09 | 930 | ROUND BAR | Incoming | Round Bar Received 45Mm Od Instead Of 50Mm. | Vendor Negligance | Warn to Purchase | 2024 | 4 | April
62 | 2024-04-09 | 930 | HEX BAR | Incoming | Hex Bar Received 22Mm Instead Of 35Mm. | Vendor Negligance | Warn to Purchase | 2024 | 4 | April
63 | 2024-04-13 | 1016 | DUCTING | Fitup | Height Of Top Duct Of Tdc Taken 550 Mm Instead Of 450Mm. | Drawing Did Not Read Carefully. |  | 2024 | 4 | April
64 | 2024-04-15 | 1017 | FWT | Fitup | Lifting Hook Fitted With Tank Without Bevelling . | Fitter Forget To Do Bevelling. |  | 2024 | 4 | April
65 | 2024-04-15 | 1024 | HOT WATER GENERATOR | Fitup | Lwss2 And Lwss3 Are Fitted In Orientation 32° And 28° Instead Of 45°. | Production Negligance |  | 2024 | 4 | April
66 | 2024-04-17 | 920 | COIL TYPE BOILER | Fitup | Smoke Outlet Connection Orientation Is 180 ° Istead Of 90°. | Production Negligance |  | 2024 | 4 | April
67 | 2024-04-22 | 1024 | OIL TANK | Marking | N5 And N8 Nozzle Orientation And Elevation Mismatch As Per Drawing. | Fitter Did Not Read Drawing Well. |  | 2024 | 4 | April
68 | 2024-05-02 | 1017 | CRS | Incoming | Mobery Of Crs Received 200Mm Cc Instead Of 178Cc. | Purchasenegligance. | Rejected | 2024 | 5 | May
69 | 2024-05-08 | 1024 | CHIMNEY | Welding | In Chimney Base Received Lot Of Under Cut .. | Taken More Current As Per Requirement.. |  | 2024 | 5 | May
70 | 2024-05-08 | 1017 | WPH | Marking | Taken Wrong Middle Line Of All Orientation. | Lack Of Knowledge About Orientation. |  | 2024 | 5 | May
71 | 2024-05-10 | GN824 | PIPE | Rusted | In 250Nb Sch80 Pipe Having Pitted And Too Much Pitted . | Vendor Negligance. | Rejected | 2024 | 5 | May
72 | 2024-05-13 | GN824 | ELECTRODE | Uneven Height of Electrode | In Electrode Having Uneven Height In Both Head. | Vendor Negligance. | Rejected | 2024 | 5 | May
73 | 2024-05-21 | 1047 | CABINET | Short width | 4 And 4A Cabinet Frame Width Short Upto 70Mm . | Vendor Negligance | Rejected | 2024 | 5 | May
74 | 2024-05-27 | GN824 | ELECTRODE | Marking | N1 Nozzle Connection Marking 25 Nb Instead Of 40Nb. | Over Confidence Of Fitter | Rejected | 2024 | 5 | May
75 | 2024-05-28 | 1057 | ECONOMISER | Nozzle orientation | Economiser Nozzles Marking Are Not As Per Tube Holes Orientation. | Lack Of Knowledge Of Fitter. | Remarked | 2024 | 5 | May
76 | 2024-06-03 | 1048 | BOILER | Fitup | N5 Nozzle Pipe Taken Sch40 Instead Of Sch80. | Lack Of Knowledge Of Fitter. | Changed | 2024 | 6 | June
77 | 2024-06-05 | 1048 | BOILER | Marking | In Perforated Header Middle Centre Hole Are Taken 200Mm Beyond As Per Design . | Over Confidence Of Fitter | Remarked | 2024 | 6 | June
78 | 2024-06-10 | 1043 | STRUCTURE | Marking | Taken Channel 50X100 Instead Of Sq.75X5Mm | Drawing Not Read Well | give knowledge about drawing | 2024 | 6 | June
79 | 2024-06-12 | 1065 | SQ. BAR | Bendness | Sq. Bar Rejected Due To Bendness Occured. | Vendor Negligance | Rejected | 2024 | 6 | June
80 | 2024-07-02 | 1048 | BOILER | Marking | N8 Nozzles Elevation Marked In Opposite To Each Other In Both Side. | Drawing Did Not Read Carefully. | Remarked | 2024 | 7 | July

## Raw Data 1
THERMODYNE ENGINEERING SYSTEMS LOG OF Error/DEFECT REPORT
SL. NO. | DATE | ORF/ JOB NO. | NAME OF EQUIPMENT/ PART | DRAWING NO. | TYPE OF Error | DETAILS OF ErrorOCCURRED | ROOT CAUSE OF ErrorOCCURRED | CORRECTIVE ACTION | METHOD OF CORRECTION | PREVENTIVE ACTION
1 | 2023-06-03 | 901 | Bag Filter |  | Porosity | Porosity defect found in corner joint of bag filter | Lack of awarness of welder | Eliminated | Grinding first and then Re-welding | Training to be imparted to the welder with respect to same Welding process & WPS
2 | 2023-06-03 | 912 | Boiler/joint of front plate |  | Porosity | Porosity defect found in corner side of boiler | Lack of awarness of welder | Eliminated | Grinding first and then re-welding | Training to be imparted to the welder with respect to same Welding process & WPS
3 | 2023-06-03 | 912 | Boiler shell/smoke box |  | Lack of fusion | Lack Fusion Found assmebly of Boiler shell & smoke box | Lack of awarness of welder | Eliminated | Fill Welding again | Re-qualification of the welder to be carried out to check the ability of the welder
4 | 2023-06-03 | 901 | Boiler |  | Porosity | Porosity defect found in corner of smoke Box | Lack of cleaning of weld joint before welder | Eliminated | Grinding first and then Re-welding | Training to be imparted to the welder with respect to same Welding process & WPS
5 | 2023-06-03 | 901 | Boiler/Nozzle |  | Poor Weld Finishing | poor weld finshing in nozzles support stiffner | wrong technique applied by welder | Eliminated by gring and welding | Re-Welding & finishing | Training to be imparted to the welder with respect to same Welding process & WPS
6 | 2023-06-08 | 901/ti-1264 | Boiler membrane tube |  | Porosity | Porosity defect found in Welding of flat with Membrane tube | Lack of awarness of welder | Removed | Grinding first and then Re-welding | Training to be imparted to the welder with respect to same Welding process & WPS
7 | 2023-06-08 | 901 | Bag filter |  | Crack | Found crack corner of bag filter to joint angle | Lack of awarness of Fitter | Eliminated | Repaired
8 | 2023-06-12 | 888 | Boiler shell |  | Crater | Some crater was found on the Bollier Shell | Lack of awarness of welder | Eliminated | Grinding first and then Re-welding | Training to be imparted to the welder with respect to same Welding process & WPS
9 | 2023-06-19 | 920 | Coil type Boiler/ Coil |  | Porosity | Porosity was found on the coil | Lack of awarness of welder
10 | 2023-06-27 | 784 | Thermic fluid heater |  | Slag | Slag was found Joint of shell | Lack of awarness of welder | Eliminated | Grinding & Finishing | Training to be imparted to the welder with respect to same Welding process & WPS
r | 2023-06-08 | 919 | Coil type Boiler/ Coil/ PRV |  | Pitted | Pitted/Locking system was not available | Lack of awarness of vendor | Rejeted | Replaced
12 | 2023-06-09 | - | Pressure gauge |  | Wrong deliverd | Recived 6"+600 mmwc in placed of-0 to-600mmwc | Lack of awarness of vendor | Rejeted | Replaced
13 | 2023-06-13 | 888 | Boiler header |  | Poor Weld Finishing | Poor weld finshing in Support of Header | Lack of awarness of welder | Eliminated | Grinding first and then Re-welding | Training to be imparted to the welder with respect to same Welding process & WPS
14 | 2023-06-14 | 912 | Boiler saddle joint |  | Poor Weld Finishing | Poor weld finshing in weld joint | Lack of awarness of welder | Eliminated | Grinding first and then Re-welding | Training to be imparted to the welder with respect to same Welding process & WPS
15 | 2023-07-08 | 901/TI-1264 | Bag Filter |  | Spatter | Found spatter on the side of the bag filter | Lack of awarness of welder | Eliminated | Grinding first and finishing | Training to be imparted to the welder with respect to same Welding process & WPS
16 | 2023-07-11 | 920/GN-767 | Coil type Boiler/ Coil |  | Porosity | Porosity was found on the coil weld area | Lack of awarness of welder | Eliminated | Grinding first and then re-welding | Training to be imparted to the welder with respect to same Welding process & WPS
17 | 2023-07-11 | 906/GN-763 | Hot air generator |  | Insulation Sheet | Insulation sheet was damaged and not fitted properly | Production | Eliminated | New insulation sheet was fitted Properly
18 | 2023-07-16 | 901/TI-1264 | Feed Water tank /Nozzle |  | Porosity | 40 NB Nozzles to shell Welding found leaked during water filling test at one point due to porosity in welding. | Lack of awarness of welder | Eliminated | Grinding first and then Re-welding | Training to be imparted to the welder with respect to same Welding process & WPS
19 | 2023-07-21 | - | Stock |  | Pitted & Broken | 5 CI Wheels are found pitted & broken | Lack of awarness of vendor | 5 Nos are Rejected | Will be Replace
20 | 2023-07-25 | 941/GN-776 | Coil type Boiler |  | Pin holes & Spatters | In coil1 & Coil 2 Some Pin holes & spatters were found on the coils | Lack of awarness of welder
21 | 2023-07-27 | 914/TI-1276 | Steam Boiler | TI-1276-BSD-13115-1/1-00 | Porosity | ORF-914, During Hydro test, found leakage in 4 tube of Boiler due to small porosity on the corner of weld | Lack of awarness of welder | Eliminated | Repaired | Training to be imparted to the welder with respect to same Welding process & WPS
22 | 2023-08-14 | 948/TI-1287 | ERW Tube (63.50x3.66mm) | TI-1287-BSD-13764-1/1-00 | Production | Dent was found is only one ERW Tube, it is not acceptable | Lack of awarness of vendor | Rejected | Replaced
23 | 2023-08-09 | 486/GN-769 | ERW Tube (63.50x3.66mm) | GN-769-TFH-60-9586-1/1-00 | Production | During filling water, found leakage in 1 tube of Boiler due to small porosity on the corner of weld | Lack of awarness of welder | Eliminated | Repaired
24 | 2023-08-11 | 555/TI-1180 | Steam Boiler | TI-1180-PP-9847-1/1-00 | Drawing | The hole distance from the center of the smoke box is given as 115 mm in the drawing but in the actualjob it is 95mm | Drawing mistake | - | -
25 | 2023-08-19 | Stock | Coil type Boiler/Spring | - | Purchase | 12.7 mm Dia spring was required as per PO, but 9.5mm dia spring was recived, Qty- 06 nos | Lack of awarness of vendor | Rejected | Replaced
26 | 2023-08-19 | 928/GN-768 | Bag Filter/Weld socket | - | Purchase | 25 mm weld socket was required as per PO, But 25 mm threaded socket was recived Qty- 30 Nos | Lack of awarness of vendor | Rejected | Replaced
27 | 2023-09-08 | 810/GN-707 | Thermic fluid heater | GN-707-APH-11436-1/1-00 | Purchase | 65 NB Short bend was found pitted, bented and dirty (10 Nos) | Lack of awarness of vendor | Rejected
28 | 2023-11-08 | -- | PRESURE GUAGE | IN STOCK | DIAL OF PREESURE GUAGE WAS BLACKISH | H-GURU MADE PRESURE GUAGE (0-42 KG/CM2) QTY=1 DIAL OF PRESURE GUAGE WAS BLACKISH AND NOT ACCEPTABLE | LACK OF AWARNESS OF WELDER | REJECTED | REPLACED
29 | 2023-12-15 | ORF-969 | ECONIMIZER |  | Welding | DURING THE INSPECTION OF ECONIMOZER STRUCTURE SHELL WELING FOUND ErrorIN L-SEAM Welding | WELDER NEGLIGANCE | ELIMINATED | REPIIRED
30 | 2023-12-15 |  | O CLAMP | IN STOOCK | Purchase | 40 mm DIA O CLAMP WAS REQUIRED BUT RECIEVED 32 MM DIA | LACK OF AWARNESS | REJECTED | REPLACED
31 | 2023-12-26 | ORF-972 | BOILER |  | Production | BOILER TUBE Welding LEAK FOUND DURING HYDRO TEST INSPECTION | WELDER NEGLIGANCE | ELIMINATED | REWORK
32 | 2024-01-01 | ORF-972 | BOILER FURNACE ENCLOSER FRONT SIDE | TI-1289-EC-14487-1/1-00 | Drawing | FURNACE ENCLOSER OF FRONT SIDE OF BOILER GIVEN WRONG DESIGN IN DRAWING . | LACK OF AWARNESS OF DRAWING DEPT. | ELIMINATED | CORRECTION IN DRAWING | DISCUSSION WITH DRAWING DEPT.
33 | 2024-01-02 | ORF-915 | BOILER WATER WALL TOP HEADER | TI-1278 | Drawing | BOILER WATER WALL TOP HEADER HOLE TO HOLE DISTANCE for tube fitting IS GIVEN WRONG BY DRAWING DEPT. | LACK OF AWARNESS OF DRAWING DEPT. | ELIMINATED | CORRECTION IN DRAWING | DISCUSSION WITH DRAWING DEPT.
34 | 2024-01-04 | ORF-994 | TUBE PLATE | TI-1299BSD-15004-1/1-00 | Drawing | TUBE PLATE HOLE DRILL DIAMETER WAS NOT GIVEN IN DRAWING | DRAWING DEPT. NEGLIGANCE | ELIMINATED | CORRECTION IN DRAWING | DISCUSSION WITH DRAWING DEPT.
35 | 2024-01-06 | ORF-980 | OIL TANK | GN-796 | Welding | TOP SIDE PLATE OF OIL TANK IS SWEELED DUE TO WRONG FITTMENT | LACK OF AWARNESS OF FITTER | REWORK | CUTTING THE PLATE AND USED NEW PLATE
36 | 2024-01-10 | STOCK | MS PLATE 2062 | -- | Purchase | MS PLATE (LXBXT)=(6300X1515X6 MM THK) WAS BEND AT MANY POINTS . | VENDOR NEGLIGANCE | REJECTED | REPLACED | WARNING GIVEN TO THE VENDOR
37 | 2024-01-11 | STOCK | CORROGATIVE SHEET | --- | Purchase | CORROGATIVE SHEET IS SCRATCHED AT MANY POINTS. | VENDOR NEGLIGANCE | REJECTED | REPLACED | GIVEN WARNING TO THE VENDOR
38 | 2024-02-01 | STOCK | ECONIMIZER | -- | Cutting | ECONOMIZER NOZEL HOLE CUTTING WAS NOT AS PER DRAWING | NEGLIGANCE | ELIMINATED | - | GIVEN WARNING TO CUTTING OPERATOR
39 | 2024-02-07 | 1009 | BOILER (RSO) | - | Production | THERMOSTAT PIPE WAS WELDED DEEP INSIDE THE OUTLET PIPE | LACK OF KNOWLWDGE | ELIMINATED | REWORK | -
| 2024-02-07 | 994 | FURNACE ENCLOSR | -- | Drawing | FURNACE ENCLOZER LENGTH WAS GIVEN IN DRAWIG 40 MM EXTRA | MIS CALCULATION OF DRAWING | REWORK' | CUTTING THE EXTRA PLATE | DISCUSSION WITH DRAWING DEPT
40 | 2024-02-07 | 994 | BOILE R | TI-1299 | Drawing | LEG HEIGHT OF BOILER WAS GIVEN WRONG IN DRAWING REQUIRED =1215 BUT GIVEN IN DRAWING =1315 | MIS CALCULATION OF DRAWING | ELIMINATED | CORRECTION IN DRAWING | DISCUSSION WITH DRAWING DEPT
41 | 2024-02-12 | 972 | FURNACE TOP PLATE | TI-1300 | Drawing | LENGTH OF FURNACE TOP PLATE WAS GIVEN WRONG IN DRAWING REQUIRED =1544 BUT GIVEN IN DRAWING =1500 | MIS CALCULATION OF DRAWING | REWORK | CORRECTION IN DRAWING
42 | 2024-02-12 | 968 | BOX COVER PLATE | GN-799 | Production | TIRMINAL BOX COVER PLATE WAS DAMAGED | PRODUCTION NEGLIGANCE | REWORK | CUTTING THE DAMAGED PLATE AND WELDED NEW PLATE
43 | 2024-02-12 | 1005 | PRS |  | Drawing | PRV CONNECTION FLANGE GIVEN IN DRAWING WAS =CLASS 300 BUT REQUIRED =CLASS 150 | Drawing | REWORK | CUT THE FLANGE AND WELDED CLASS 150 FLANGE | DISCUSSION WITH DRAWING DEPT
44 | 2024-02-12 | STOCK | MS SOCKET | - | Purchase | MS SOCKET REJECTED DUE TO RUSTED FROM OUTSIDE AND INSIDE | VENDOR NEGLIGANCE | REJECTED | REPLACED | WARNING TO VENDOR
45 | 2024-02-13 | STOCK | PULLY 3.5" 90 OD |  | Purchase | PULLY REJECTED DUE TO OUTER DIA WAS NOT MATCHED REQUIRED OUTER DIA =90 BUT OBSERVED OUTER DIA =84 | VENDOR NEGLIGANCE | REJECTED
46 | 2024-02-20 | 994 | BOILER SHELL | TI-1299 | Welding | WELDER LEFT THE Welding IN SADDLE TO SHELL JOINT | WELDER NEGLIGANCE | ELIMINATED | INSTANT Welding DONE | GIVEN WARNING TO VENDOR FOR FUTURE
47 | 2024-02-26 | 960 | BOILER SHELL | TI-1290 | Drawing | FEED LINE OF BOIELR SHELL GIVEN 40MM EXTRA IN DRAWING | MIS CALCULATION OF DRAWING | ELIMINATED | INSTANT REWORK THE FEED LINE | DISCUSSION WITH DRAWING DEPT
48 | 2024-03-12 | 968 | Hot Water Generator | GN-799 | Mismatch | Rockwool pad Batch number mismatched from mtc | Mis typing by vendor | Elimated | Rechanged | GIVEN WARNING TO VENDOR FOR FUTURE
49 | 2024-03-13 | 968 | Hot Water Generator | GN-799 | Leakage | During hydro testing of heat water generator found 05 heater element leakage. | Poor brazzing Welding | Replaced to vendor
50 | 2024-03-15 | 968 | Hot Water Generator | GN-799 | Leakage | During hydro testing of heat water generator found 03 heater element leakage. | Poor brazzing Welding | Replaced to vendor
51 | 2024-03-16 | ORF-1019 | Feed Water tank |  | Marking | During inspection of nozzle marking found 15NB socket marking missing in front of tank . | Proper did not check drawing | Remarking
52 | 2024-03-18 | 1022 | Boiler | TI-1304-1/1-00 | Marking | Width of furnace shell plate beyond upto 08mm as per drawing. | PRODUCTION NEGLIGANCE | Rework | Remarking of width
53 | 2024-03-22 | 1011 | Water Tank | GN-815-FWT-1/1-00 | Fitup | Saddle centre to centre distance beyond upto 12mm as per design | PRODUCTION NEGLIGANCE | Warn to fitter | Changed as per design. | Given training to fitter of saddle centre to
54 | 2024-03-23 | 1020 | Coil type Boiler | GN-814-COIL TYPE-1/1-00 | Fitup | Optimiser flange under thickness fittted need 14mm thick flange but fitted 12mm thick. | PRODUCTION NEGLIGANCE | Warn to fitter |  | Gven training to fitter how to read flange
55 | 2024-03-28 | 1014 | APH | GN-818-APH-1/1-00 | Fitup | Baffle of Mddle shell of aph fitted in opposite tube plate that reason orientation of hole are not matched as per drawing . | PRODUCTION NEGLIGANCE | Warn to fitter | All Connection marked as per baffle plate . | Given training to fitter of connection fitup as
56 | 2024-03-28 | 1014 | Dariation Tank | GN-818-dariation tank-1/1- 00 | Fitup | Fluid inlet flange is not in level and also projection of flange short upto 05 mm . | PRODUCTION NEGLIGANCE | Warn to fitter | Refitted | Given training to fitter of connection fitup as
| 2024-04-01 | 1034 | Chimney | GN-826-Chimney-1/1-00 | Incoming | Lot of rust occured on pipe of chimney ,size is 200NB | VENDOR NEGLIGANCE | Warn to Purchase
57 | 2024-04-05 | 1016 | Coil Bottom reducer |  | Rolled | We need Ø1311 mm OD but we find out Ø1105mm and bottom side we need Ø580mm but we find out Ø412mm. | Layout showing in drawing is wrong . | Warn to Design Team | Before giving drawing to fitter first check by themself.
58 | 2024-04-05 | 1016 | I beam | GN-820-Dumping Grade-1/1-0 | Incoming Incoming | I beam received upto 10mm bend.. | VENDOR NEGLIGANCE | Warn to Purchase
59 | 2024-04-09 | 1026 | Control Panel | ...... |  | Panel back hole out upto 10mm | VENDOR NEGLIGANCE | Warn to Purchase
60 | 2024-04-09 | 930 | Round Bar | ...... | Incoming | Round bar received 45mm OD instead of 50mm. | VENDOR NEGLIGANCE | Warn to Purchase
61 | 2024-04-09 | 930 | Hex Bar | ...... | Incoming | Hex bar received 22mm instead of 35mm. | VENDOR NEGLIGANCE | Warn to Purchase
62 | 2024-04-13 | 1016 | Ducting | GN-820-DD-1/1-00 | Fitup | Height of top duct of tdc taken 550 mm instead of 450mm. | Drawing did not read carefully.
63 | 2024-04-15 | 1017 | FWT | TI-1303-FWT-1/1-00 | Fitup | lifting hook fitted with tank without bevelling . | Fitter forget to do bevelling.
64 | 2024-04-15 | 1024 | Hot water Generator | GN-822-HWG-1/1-00 | Fitup | LWSS2 AND LWSS3 are fitted in orientation 32° and 28° instead of 45°. | PRODUCTION NEGLIGANCE
65 | 2024-04-17 | 920 | Coil Type Boiler | GN-767-COIL TYPE-1/1-00 | Fitup | Smoke outlet Connection orientation is 180 ° istead of 90°. | PRODUCTION NEGLIGANCE
66 | 2024-04-22 | 1024 | OIL TANK | GN-822-OIL TANK-1/1-00 | Marking | N5 and N8 nozzle orientation and elevation mismatch as per Drawing. | Fitter did not read drawing well.
67 | 2024-05-02 | 1017 | CRS | TI-1303-CRS-1/1-00 | Incoming | Mobery of CRS received 200mm CC instead of 178CC. | PurchaseNegligance. | Rejected
68 | 2024-05-08 | 1024 | CHIMNEY | GN-822-CHIMNEY-1/1-00 | Welding | In Chimney base received lot of under cut .. | Taken more current as per requirement.. |  |  | Warn to welder to will not do this type of
69 | 2024-05-08 | 1017 | WPH | TI-1303-WPH-1/1-00 | Marking | Taken wrong middle line of all orientation. | lack of knowledge about orientation.
70 | 2024-05-10 | GN-824 | Pipe | GN-824 | Rusted | In 250NB sch80 pipe having pitted and too much pitted . | Vendor Negligance. | Rejected
71 | 2024-05-13 | GN-824 | Electrode | GN-824 | Uneven Height of Electrode | In electrode having uneven height in both head. | Vendor Negligance. | Rejected
72 | 2024-05-21 | 1047 | Cabinet | GN-831-CABINET-1/1-00 | Short width | 4 and 4A Cabinet frame width short upto 70mm . | VENDOR NEGLIGANCE | Rejected
73 | 2024-05-27 | GN-824 | Electrode Header | GN-824-EN-1/1-00 | Marking | N1 nozzle connection marking 25 NB instead of 40NB. | over confidence of fitter | Rejected
74 | 2024-05-28 | 1057 | Economiser | GN-834-PP-1/1-00 | Nozzle orientation | Economiser nozzles marking are not as per tube holes orientation. | lack of knowledge of fitter. | Remarked
75 | 2024-06-03 | 1048 | Boiler | TI-1309-BSD-1/1-00 | Fitup | N5 Nozzle pipe taken sch40 instead of sch80. | lack of knowledge of fitter. | Changed
76 | 2024-06-05 | 1048 | Boiler | TI-1309-BSD-1/1-00 | Marking | In Perforated header middle centre hole are taken 200mm beyond as per design . | Over confidence of fitter | Remarked
77 | 2024-06-10 | 1043 | Structure | GN-829-SD-1/1-00 | Marking | taken channel 50x100 instead of sq.75x5mm | Drawing not read well | give knowledge about drawing
78 | 2024-06-12 | 1065 | SQ. Bar | TI-1282-1/1-00 | Bendness | Sq. bar rejected due to bendness occured. | VENDOR NEGLIGANCE | Rejected
79 | 2024-07-02 | 1048 | Boiler | TI-1309-BSD-1/1-00 | Marking | N8 nozzles elevation marked in opposite to each other in both side. | Drawing did not read carefully. | Remarked
80 | 2024-07-02 | 1048 | Boiler | TI-1309-BSD-1/1-00 | Marking | N8 nozzles elevation marked in opposite to each other in both side. | Drawing did not read carefully. | Remarked
81 | 2024-07-02 | 1048 | Boiler | TI-1309-BSD-1/1-00 | Marking | N8 nozzles elevation marked in opposite to each other in both side. | Drawing did not read carefully. | Remarked
82 | 2024-07-03 | 1063 | Y Strainer | ........... | Wrong Size | Y Strainer received 40NB instead of 25NB. | NEGLIGANCE
83 | 2024-07-04 | 1062 | Membrane |  | Fitup | Membrane bottom header diagonal distance having 05 mm differance in both side. | Not taken point of checking in between two holes. | Remarked of centre
84 | 2024-07-06 | 1048 | BSD | TI-1309-BSD-1/1-00 | Fitup | Man hole projection taken 50mm instead of 40mm. | Drawing did not read carefully. | Refitted
85 | 2024-07-22 | 1062 | Boiler | GN-837-BSD-1/1-00 | Fitup | N8 nozzles are not in leveled. !!!!! | After Welding stitches the nozzle of N8 is swifted. | Reffited
86 | 2024-07-21 | 1062 | Chimney | GN-837-CHIMNEY-1/1-00 | Fitup | Chimney shell uneven dia after Welding ...!!! | not get much attention on shell after welding. | Repaired
87 | 2024-08-02 | 1067 | Boiler | GN-840-EEB-1/1-00 | Drawing | N1 nozzle connection pipe is short from end of cabinet ... | short distance showing in drawing . | Changed of pipe
88 | 2024-08-04 | 1043 | Coil Shell | GN-829-COIL-1/1-00 | Drawing | Shell bottom connection dia showing 1040mm instead of 885mm. | Doing copy paste of drawing. | make correction on drawing.
89 | 2024-08-05 | 1062 | Chimney | GN-837-CHIMNEY-1/1-00 | Welding | In chimney base having under cut upto 1mm deep and also having uneven welding. | Taken more current as per requirement.. | Given trainning to welder.
90 | 2024-08-12 | 915 | FE | TI--1278-FE-1/1-00 | Drawing | in front and rear frame did not given angle support for Ash door. | Copy paste of drawing ..
91 | 2024-08-18 | 1015 | FE | GN-819-1/1-00 | Fitup | Front and rear frame did not reduce channel size ...!!!! | He has not knowledge about it..!!
92 | 2024-08-19 | 915 | BSD | GN-1278-BSD-13109-1/1-00 | Fitup | Blowdown line fitted in opposite direction as per drawing. | Fitter did not read drawing well. | Refitted
93 | 2024-08-22 | 915 | Front smoke box | GN-1278-BSD-13109-1/1-00 | Welding | Smoke box uneven Welding done.
94 | 2024-08-25 | 965 | Furnace | TI-1304-BSD-1/1-00 | Welding | Furnace stiffner ring weling having lot of spatters and also having lot of under cut. | Taken more current as per wp | rewelded
95 | 2024-09-09 | 1076 | Boiler | TI-1311-BSD-1/1-00 | Drawing | Smoke box fitup with boiler did not show in Cabinet drawing. | Copy/paste of drawing.. | Inform to drawing department
96 | 2024-09-09 | 1084 | Boiler | TI-1314-BSD-1/1-00 | Drawing | Smoke box fitup with boiler did not show in Cabinet drawing. | Copy/paste of drawing.. | Inform to drawing department
97 | 2024-09-06 | 915 | Chimney | TI-1278-BSD-1/1-00 | Welding | uneven welding | negligency | dressup of Welding
98 | 2024-09-16 | 1081 | Boiler | GN-847-PP-1/1-00 | Fitup | Outlet and inlet header connection are opposite fitted as per design | drawing did not read carefully | Refitted
99 | 2024-09-17 | 1081 | Boiler | GN-847-PP-1/1-00 | Fitup | Panel frame fitted in bottom side instead of middle of shell | drawing did not read carefully
100 | 2024-09-18 | 1081 | Boiler | GN-847-PP-1/1-00 | Drawing | Ladder orientation are showing 270° which is stucked with pump frame.
101 | 2024-09-19 | 965 | Bottom header of membrane | TI-1304-BSD-1/1-00 | Marking | Bottom header first hole marked 90mm instead of 64mm.. | drawing did not read carefully
102 | 2024-10-01 | 1084 | Boiler | TI-1311-BSD-1/1-00 | Marking | mud hole marking 200NB instead of 150NB in both side | drawing did not read carefully | Remarking
103 | 2024-10-05 | 1084 | Boiler | TI-1311-BSD-1/1-00 | Marking | N8 nozzle marking in centre line of upper n5 nozzle. | fitter neglegency | Remarking
104 | 2024-10-15 | 1076 | Membrane header | TI-1311-WWD1-15665-00 | Marking | top header and bottom header having 20mm distance long becuase in both header 20mm blind plate distance did not reduce. | drawing did not read carefully | Remarking
105 | 2024-11-03 | 1076 | Cabinet | TI-1311-CABINET-15665-00 | Fitup | Top side plate did not fitted with cabinet ...!!! | drawing did not read carefully | Fitted
106 | 2024-11-07 | 1102 | FWT | TI-1305-FWTS-1/1-00 | Marking | Hole marking pitch distance taken from outer side instead of inner side...!!! | drawing did not read carefully | Fitted
107 | 2024-11-12 | 1086 | Screw Feeder | GN-851-SF-1/1-00 | Fitup | gear box fitted with ratio 30 instead of 70 ratio.. | drawing did not read carefully | Fitted
108 | 2024-11-12 | 1107 | Electric Boiler | GN-861-EB-1/1-00 | Fitup | Sensor pocket did not fitted on steam outlet header...!! | drawing did not read carefully | Fitted
109 | 2024-12-02 | 1097 | Boiler | TI-1317-BSD-1/1-00 | Fitup | Fusible plug socket did not weld before tube insertion . | fitter neglegency | fitted and welded
110 | 2024-12-17 | ... | Electric Boiler | .... | Incoming | pipe thickness need 9.27mm but received 4.3mm ,pipe size is 250nb sch40... | vendor neglegency | rejected
111 | 2024-12-19 | 992 | Spare part(Boiler top plate) |  | Fitup | surrounded plate fitted ms instead of ms ..!!! | fitter neglegency | refitted
112 | 2024-12-24 | 1043 | Screw Feeder | GN-829-SFD-15504-00 | Fitup | Gear box fitted with ratio 100 instead of 70 ratio.. | fitter & store neglegency | changed
113 | 2024-12-28 | 1115 | Boiler | TI-1318-BSD-1/1-00 | Marking | Mud holes marking opposite to each other in both side | Plan view did not check carefuly | Remarking
114 | 2025-01-08 | 1017 | CRS | TI-1303-CRS-1/1-00 | Fitup | Insulation rock wool pad was fitted density 48kg/m3 instead of 96 kg/m3. | Technician did not clear about rockwool pad with store incharge. | changed
115 | 2025-01-09 | 1026 | Boiler | GN-877-PP-1/1-00 | Fitup | N5 nozzle connection fitted 25NB instead of 20NB . | drawing did not read carefully | Changed
116 | 2025-01-09 | 1094 | CRS | TI-1315-PP-1/1-00 | Fitup | CRS Shell width is 40mm extra. | fitter confuse for taken dimensions. | cutted the extra part of shell
117 | 2025-01-23 | 1048 | Boiler | TI-1308-PP-1/1-00 | Fitup | Top header blind end plate fitted outside of header instead of inside | drawing did not read carefully | Changed in drawing with permission of DDB sir
118 | 2025-02-17 | 1115 | FURNACE ENCLOSR | TI-1318-FE-1/1-00 | Fitup | MS door fitted instead of CI fire door in front side | drawing did not read carefully
119 | 2025-02-19 | 1094 | Top header | TI-1315-PP-1/1-00 | Marking | Top header marked 150NB instead of 125NB .... | drawing did not read carefully
120 | 2025-02-22 | 1025 | membrane | TI-1322-WWD-1/1-00 | Welding | membrane bottom side Welding did not fully complete | welder neglengency | inform to welder about their problem.
121 | 2025-03-03 | 1159 | Boiler | GN-896-PP-1/1-00 | Fitup | ms tube fitted instead of ss in economiser. | drawing did not read carefully
122 | 2025-03-15 | 1140 | Boiler shell | GN-887-PP-1/1-00 | Fitup | going to fit refractory 75mm instead of 50mm. | drawing did not read carefully
123 | 2024-07-02 | 1048 | Boiler | TI-1309-BSD-1/1-00 | Marking | N8 nozzles elevation marked in opposite to each other in both side. | Drawing did not read carefully. | Remarked
124 | 2024-07-02 | 1048 | Boiler | TI-1309-BSD-1/1-00 | Marking | N8 nozzles elevation marked in opposite to each other in both side. | Drawing did not read carefully. | Remarked
125 | 2024-07-02 | 1048 | Boiler | TI-1309-BSD-1/1-00 | Marking | N8 nozzles elevation marked in opposite to each other in both side. | Drawing did not read carefully. | Remarked
126 | 2024-07-02 | 1048 | Boiler | TI-1309-BSD-1/1-00 | Marking | N8 nozzles elevation marked in opposite to each other in both side. | Drawing did not read carefully. | Remarked
127 | 2024-07-02 | 1048 | Boiler | TI-1309-BSD-1/1-00 | Marking | N8 nozzles elevation marked in opposite to each other in both side. | Drawing did not read carefully. | Remarked
128 | 2024-07-02 | 1048 | Boiler | TI-1309-BSD-1/1-00 | Marking | N8 nozzles elevation marked in opposite to each other in both side. | Drawing did not read carefully. | Remarked
129 | 2024-07-02 | 1048 | Boiler | TI-1309-BSD-1/1-00 | Marking | N8 nozzles elevation marked in opposite to each other in both side. | Drawing did not read carefully. | Remarked
130 | 2024-07-02 | 1048 | Boiler | TI-1309-BSD-1/1-00 | Marking | N8 nozzles elevation marked in opposite to each other in both side. | Drawing did not read carefully. | Remarked
131 | 2024-07-02 | 1048 | Boiler | TI-1309-BSD-1/1-00 | Marking | N8 nozzles elevation marked in opposite to each other in both side. | Drawing did not read carefully. | Remarked
132 | 2024-07-02 | 1048 | Boiler | TI-1309-BSD-1/1-00 | Marking | N8 nozzles elevation marked in opposite to each other in both side. | Drawing did not read carefully. | Remarked
133 | 2024-07-02 | 1048 | Boiler | TI-1309-BSD-1/1-00 | Marking | N8 nozzles elevation marked in opposite to each other in both side. | Drawing did not read carefully. | Remarked
134 | 2024-07-02 | 1048 | Boiler | TI-1309-BSD-1/1-00 | Marking | N8 nozzles elevation marked in opposite to each other in both side. | Drawing did not read carefully. | Remarked
135 | 2024-07-02 | 1048 | Boiler | TI-1309-BSD-1/1-00 | Marking | N8 nozzles elevation marked in opposite to each other in both side. | Drawing did not read carefully. | Remarked
136 | 2024-07-02 | 1048 | Boiler | TI-1309-BSD-1/1-00 | Marking | N8 nozzles elevation marked in opposite to each other in both side. | Drawing did not read carefully. | Remarked
137 | 2024-07-02 | 1048 | Boiler | TI-1309-BSD-1/1-00 | Marking | N8 nozzles elevation marked in opposite to each other in both side. | Drawing did not read carefully. | Remarked
138 | 2024-07-02 | 1048 | Boiler | TI-1309-BSD-1/1-00 | Marking | N8 nozzles elevation marked in opposite to each other in both side. | Drawing did not read carefully. | Remarked
139 | 2024-07-02 | 1048 | Boiler | TI-1309-BSD-1/1-00 | Marking | N8 nozzles elevation marked in opposite to each other in both side. | Drawing did not read carefully. | Remarked
140 | 2024-07-02 | 1048 | Boiler | TI-1309-BSD-1/1-00 | Marking | N8 nozzles elevation marked in opposite to each other in both side. | Drawing did not read carefully. | Remarked
141 | 2024-07-02 | 1048 | Boiler | TI-1309-BSD-1/1-00 | Marking | N8 nozzles elevation marked in opposite to each other in both side. | Drawing did not read carefully. | Remarked
142 | 2024-07-02 | 1048 | Boiler | TI-1309-BSD-1/1-00 | Marking | N8 nozzles elevation marked in opposite to each other in both side. | Drawing did not read carefully. | Remarked

## Raw Data 2
THERMODYNE ENGINEERING SYSTEMS LOG OF Error/DEFECT REPORT
SL. NO. | DATE | ORF/ JOB NO. | NAME OF EQUIPMENT/ PART | DRAWING NO. | TYPE OF Error | DETAILS OF ErrorOCCURRED | ROOT CAUSE OF ErrorOCCURRED | CORRECTIVE ACTION | METHOD OF CORRECTION | PREVENTIVE ACTION
80 | 2024-07-03 | 1063 | Y Strainer | ........... | Wrong Size | Y Strainer received 40NB instead of 25NB. | NEGLIGANCE
81 | 2024-07-04 | 1062 | Membrane |  | Fitup | Membrane bottom header diagonal distance having 05 mm differance in both side. | Not taken point of checking in between two holes. | Remarked of centre
82 | 2024-07-06 | 1048 | BSD | TI-1309-BSD-1/1-00 | Fitup | Man hole projection taken 50mm instead of 40mm. | Drawing did not read carefully. | Refitted
83 | 2024-07-22 | 1062 | Boiler | GN-837-BSD-1/1-00 | Fitup | N8 nozzles are not in leveled. !!!!! | After Welding stitches the nozzle of N8 is swifted. | Reffited
77 | 2024-07-21 | 1062 | Chimney | GN-837-CHIMNEY-1/1-00 | Fitup | Chimney shell uneven dia after Welding ...!!! | not get much attention on shell after welding. | Repaired
78 | 2024-08-02 | 1067 | Boiler | GN-840-EEB-1/1-00 | Drawing | N1 nozzle connection pipe is short from end of cabinet ... | short distance showing in drawing . | Changed of pipe
79 | 2024-08-04 | 1043 | Coil Shell | GN-829-COIL-1/1-00 | Drawing | Shell bottom connection dia showing 1040mm instead of 885mm. | Doing copy paste of drawing. | make correction on drawing.
80 | 2024-08-05 | 1062 | Chimney | GN-837-CHIMNEY-1/1-00 | Welding | In chimney base having under cut upto 1mm deep and also having uneven welding. | Taken more current as per requirement.. | Given trainning to welder.
81 | 2024-08-12 | 915 | FE | TI--1278-FE-1/1-00 | Drawing | in front and rear frame did not given angle support for Ash door. | Copy paste of drawing ..
82 | 2024-08-18 | 1015 | FE | GN-819-1/1-00 | Fitup | Front and rear frame did not reduce channel size ...!!!! | He has not knowledge about it..!!
83 | 2024-08-19 | 915 | BSD | GN-1278-BSD-13109-1/1-00 | Fitup | Blowdown line fitted in opposite direction as per drawing. | Fitter did not read drawing well. | Refitted
84 | 2024-08-22 | 915 | Front smoke box | GN-1278-BSD-13109-1/1-00 | Welding | Smoke box uneven Welding done.
85 | 2024-08-25 | 965 | Furnace | TI-1304-BSD-1/1-00 | Welding | Furnace stiffner ring weling having lot of spatters and also having lot of under cut. | Taken more current as per wp | rewelded
86 | 2024-09-09 | 1076 | Boiler | TI-1311-BSD-1/1-00 | Drawing | Smoke box fitup with boiler did not show in Cabinet drawing. | Copy/paste of drawing.. | Inform to drawing department
87 | 2024-09-09 | 1084 | Boiler | TI-1314-BSD-1/1-00 | Drawing | Smoke box fitup with boiler did not show in Cabinet drawing. | Copy/paste of drawing.. | Inform to drawing department
88 | 2024-09-06 | 915 | Chimney | TI-1278-BSD-1/1-00 | Welding | uneven welding | negligency | dressup of Welding
89 | 2024-09-16 | 1081 | Boiler | GN-847-PP-1/1-00 | Fitup | Outlet and inlet header connection are opposite fitted as per design | drawing did not read carefully | Refitted
90 | 2024-09-17 | 1081 | Boiler | GN-847-PP-1/1-00 | Fitup | Panel frame fitted in bottom side instead of middle of shell | drawing did not read carefully
91 | 2024-09-18 | 1081 | Boiler | GN-847-PP-1/1-00 | Drawing | Ladder orientation are showing 270° which is stucked with pump frame.
92 | 2024-09-19 | 965 | Bottom header of membrane | TI-1304-BSD-1/1-00 | Marking | Bottom header first hole marked 90mm instead of 64mm.. | drawing did not read carefully
93 | 2024-10-01 | 1084 | Boiler | TI-1311-BSD-1/1-00 | Marking | mud hole marking 200NB instead of 150NB in both side | drawing did not read carefully | Remarking
94 | 2024-10-05 | 1084 | Boiler | TI-1311-BSD-1/1-00 | Marking | N8 nozzle marking in centre line of upper n5 nozzle. | fitter neglegency | Remarking
95 | 2024-10-15 | 1076 | Membrane header | TI-1311-WWD1-15665-00 | Marking | top header and bottom header having 20mm distance long becuase in both header 20mm blind plate distance did not reduce. | drawing did not read carefully | Remarking
96 | 2024-11-03 | 1076 | Cabinet | TI-1311-CABINET-15665-00 | Fitup | Top side plate did not fitted with cabinet ...!!! | drawing did not read carefully | Fitted
97 | 2024-11-07 | 1102 | FWT | TI-1305-FWTS-1/1-00 | Marking | Hole marking pitch distance taken from outer side instead of inner side...!!! | drawing did not read carefully | Fitted
98 | 2024-11-12 | 1086 | Screw Feeder | GN-851-SF-1/1-00 | Fitup | gear box fitted with ratio 30 instead of 70 ratio.. | drawing did not read carefully | Fitted
99 | 2024-11-12 | 1107 | Electric Boiler | GN-861-EB-1/1-00 | Fitup | Sensor pocket did not fitted on steam outlet header...!! | drawing did not read carefully | Fitted
100 | 2024-12-02 | 1097 | Boiler | TI-1317-BSD-1/1-00 | Fitup | Fusible plug socket did not weld before tube insertion . | fitter neglegency | fitted and welded
101 | 2024-12-17 | ... | Electric Boiler | .... | Incoming | pipe thickness need 9.27mm but received 4.3mm ,pipe size is 250nb sch40... | vendor neglegency | rejected
102 | 2024-12-19 | 992 | Spare part(Boiler top plate) |  | Fitup | surrounded plate fitted ms instead of ms ..!!! | fitter neglegency | refitted
103 | 2024-12-24 | 1043 | Screw Feeder | GN-829-SFD-15504-00 | Fitup | Gear box fitted with ratio 100 instead of 70 ratio.. | fitter & store neglegency | changed
104 | 2024-12-28 | 1115 | Boiler | TI-1318-BSD-1/1-00 | Marking | Mud holes marking opposite to each other in both side | Plan view did not check carefuly | Remarking
105 | 2025-01-08 | 1017 | CRS | TI-1303-CRS-1/1-00 | Fitup | Insulation rock wool pad was fitted density 48kg/m3 instead of 96 kg/m3. | Technician did not clear about rockwool pad with store incharge. | changed
106 | 2025-01-09 | 1026 | Boiler | GN-877-PP-1/1-00 | Fitup | N5 nozzle connection fitted 25NB instead of 20NB . | drawing did not read carefully | Changed
107 | 2025-01-09 | 1094 | CRS | TI-1315-PP-1/1-00 | Fitup | CRS Shell width is 40mm extra. | fitter confuse for taken dimensions. | cutted the extra part of shell
108 | 2025-01-23 | 1048 | Boiler | TI-1308-PP-1/1-00 | Fitup | Top header blind end plate fitted outside of header instead of inside | drawing did not read carefully | Changed in drawing with permission of DDB sir
109 | 2025-02-17 | 1115 | FURNACE ENCLOSR | TI-1318-FE-1/1-00 | Fitup | MS door fitted instead of CI fire door in front side | drawing did not read carefully
110 | 2025-02-19 | 1094 | Top header | TI-1315-PP-1/1-00 | Marking | Top header marked 150NB instead of 125NB .... | drawing did not read carefully
111 | 2025-02-22 | 1025 | membrane | TI-1322-WWD-1/1-00 | Welding | membrane bottom side Welding did not fully complete | welder neglengency | inform to welder about their problem.
112 | 2025-03-03 | 1159 | Boiler | GN-896-PP-1/1-00 | Fitup | ms tube fitted instead of ss in economiser. | drawing did not read carefully
113 | 2025-03-15 | 1140 | Boiler shell | GN-887-PP-1/1-00 | Fitup | going to fit refractory 75mm instead of 50mm. | drawing did not read carefully
114
115
116
117
118
109
110
111
112
113
114
115
116
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131